## Sheet1
Sr. no. | Point | Remark | Responsibility | Remarks after discussion with Vaibhav sir | Plan from portal | RFC STATUS | Responcible | Detail | Status
1 | Pack Size Master or Manual | Master with editable field for 2 months. | Mawai | Deliverable but data maintained in SAP will reflect in portal ,in editable format | will delivered on 23 th december | has to edit in Existing RFC | Rajat | Add packing stadered field in RFC
|  | For Master maintenance ,based upon Purchase group data will be provided by IT | Bsikka |  | will delivered on 23 th december
|  | Master will be completed by 15 Dec 2019 | Ssharma |  | will delivered on 23 th december
2 | Barcode information | item code, qty , vendor name, Po no, Invoice Date. | Mawai | Deliverable | will delivered on 23 th december | Not required | Vipin | Vendor code has to be added in bar code | Done
3 | Gate Entry process incorporation | Demo will be provided | Mawai | Demo is provided | will delivered on 23 th december
|  | All the report name where ever changes required will be shared for In transit information in between Gate entry and receipt with IT | Kbahal |  | will delivered on 23 th december
4 | Excess Material Handling Process | Fresh Invoice will be called off for Gate entry generation. | Mawai | If vendor bill include full quantity then new invoice required before GRN. | will delivered on 23 th december
|  | Excess material handling in Gate entry process will be further explore during gate entry demo. | Mawai | Demo is provided, for excess quantity ,which is not include in vendor bill new invoice is required ,if quantity is include in vendor bill then it is business call weather they required two new invoice or accept the same . | will delivered on 23 th december
5 | Vendor capacity | Report format need to be shared with IT by 29 NOV 2019 | Kbahal | manual point | will delivered on 23 th december |  | Vipin | Has to addd column for material vendor capicity | Done
6 | Mass email | Email work flow for common document share such as vendor policy | Mawai | Deliverable for all Vendors which are on portal. | will delivered on 23 th december | Not required | Vipin | has to be implemented | Done
|  | This will be only applicable for those vendors who are already exists in vendor portal and email format draft need to share with IT | SSHARMA |  | will delivered on 23 th december
7 | Vendor Dashboard | All critical information need to share with IT (landing page after login) by 10 DEC 2019 | Kbahal | Deliverable | Required from GROZ |  | GROZ | required from groz
8 | Supplier corrective Action | Accurate Point, They need option where Supplier can enter corrective action no. and upload the pdf file. | Mawai | Deliverable , but the size of data base will affect by this , need more data base storage | will delivered on 23 th december | Not required | Vipin | has to be developed/ format required from groz
9 | Drawing | Accurate Point, DWG no. is maintained in MM03 and they have internal control to maintain the updated no. in master | Aparashar | Deliverable but Size of data base will be affected. | will delivered on 23 th december | NEW RFC REQUIRED | Rajat | Material master drawing RFC requird.
10 | Vendor Rating | Existing /amended logic will be shared with IT 15 DEC 2019 | Kbahal | Vendor rating can be provided on portal as in SAP but if there are some manual input parameters that must be maintained manually. | Required from GROZ |  | GROZ | formula required
11 | Urgent Qty | Scaling factor or item vendor combination logic will be shared with IT 2 DEC 2019 | kbahal/bsikka | Manual activities has to be done ,have to maintain priority of schedule so that it will reflect on vendor portal | Required from GROZ |  | GROZ | required from groz
12 | Vendor Actual Pendency | Fresh format of vendor requirement by 29 NOV 2019 | KBAHAL | Can be execute but Size of data base will be affected. | Required from GROZ |  | GROZ | required from groz
13 | Schedule update time | Date selection criteria.. To ..from | Mawai | Deliverable ,schedule of vendor can be seen on portal as per mentioned selection criteria. | will delivered on 23 th december | Not required | Vipin | will developed in portal
|  | Detail Sheet |  |  | will delivered on 23 th december
|  | Consolidated Sheet |  |  | will delivered on 23 th december
|  | PO/SA automation email work flow in SAP. | Bsikka |  | Required from GROZ |  | GROZ | required from groz
14 | Schedule file upload | provision for pdf update | Mawai | Deliverable, but Size of data base will be affected. | will delivered on 23 th december |  | Vipin | will developed in portal
|  | 3 month pdf storage | Mawai |  | will delivered on 23 th december |  | Vipin | will developed in portal
100001
900300302
8787
1007
10001